- Partnership Agreement

- Acronym:TRANSDANUBE

Project title: Sustainable Transport and Mobility 
in Tourism Regions along the Danube

| European Territorial Co-operation 2007 – 2013 |  |
| --- | --- |

- Partnership Agreement

for the implementation of the project

TRANSDANUBE

Sustainable Transport and Mobility 
in Tourism Regions along the Danube

within the

South East Europe Transnational Cooperation Programme (SEE)

between

- Lead Partner

Umweltbundesamt GmbH (Environmental Agency Austria), 	
Spittelauer Lände 5; 1090 Vienna, Austria

and

- ERDF Project Partner 1

DIE DONAU - Internationale Touristische Werbegemeinschaft (Danube Tourist Commission) Wiedner Hauptstraße 120-124/ 4. OG, 1050 Vienna, Austria

- ERDF Project Partner 2

Amt der Burgenländischen Landesregierung (Regional government of Burgenland)

Europaplatz 1, 7000 Eisenstadt, Austria

- ERDF Project Partner 3

Bratislavský samosprávny kraj (Bratislava Self-Governing Region)

Sabinovská 16; 820 05 Bratislava, Slovensko

- ERDF Project Partner 4

Nyugat-Pannon Terület- és Gazdaságfejlesztési Szolgáltató Nonprofit Kft. (West Pannon Regional and Economic Development Nonprofit Ltd.)

Horváth Boldizsár krt. 9, H-9700 Szombathely, HUNGARY

- ERDF Project Partner 5

BBTDM, Bakony és Balaton Térségi Turisztikai Nonprofit Korlátolt Felelősségű Társaság (Bakony and Balaton Regional Tourism Nonprofit Ltd)

Óváros tér 2, 8200 Veszprém

- ERDF Project Partner 6

Областна администрация Видин  (Vidin Regional Administration)

6, Dunavska Str., 3700 Vidin, Republic of Bulgaria

- ERDF Project Partner 7

Клуб „Устойчиво развитие на гражданското общество” (Club Sustainable Development for Civil Society)

28-A, Dospat Str., Sofia-1463, BULGARIA

- ERDF Project Partner 8

Institutul National de Cercetare-Dezvoltare in Turism (National Institute for Research and Development in Tourism)

Apolodor 17, 050741 Bucharest, Romania

- ERDF Project Partner 9

ADR SE - Agentia pentru Dezvoltare Regionala Sud-Est (SE RDA - The Regional Development Agency of the South-East Development Region)

24 Anghel Saligny Street; 810118 Braila, Romania

- ERDF Project Partner 10

Slovensky cykloklub – SCK (Slovak cycle club - SCC)

Namestie slobody 6, 921 01 Piestany

20% ERDF Project Partner 1

Donaubüro gemeinnützige GmbH (Danube Office Ltd.), 	
Kronengasse 4/3, 89073 Ulm; Germany

- IPA Partner 1

Dunavski centart za kompetenciju (Danube Competence Centre)

Cika Ljubina 8/I, 11000 Belgrade, Serbia

- IPA Partner 2

RARIS-Regionalna agencija za razvoj istocne Srbije 	
(Regional Development Agency Eastern Serbia)

Trg Oslobodenja 1, 19000 Zajecar/Srbija, Serbia

- EU Associated 1

- Stadtgemeinde Neusiedl am See (Municipality Neusiedl am See)

Hauptplatz 1, Neusiedl am See, 7100 Austria

- EU Associated 2

Ministerstvo dopravy, výstavby a regionálneho rozvoja Slovenskej republiky (Ministry of Transport, Construction and Regional Development of the Slovak Republic)

- Námestie slobody č. 6; 810 05 Bratislava, Slovak Republic

- EU Associated 3

Regionálna rozvojová agentúra Senec – Pezinok (Regional Development Agency Senec Pezinok)
Kysucka 14, 903 01 Senec, Slovakia

EU Associated 4

GYMSMÖ – Gyır-Moson-Sopron Megyei Önkormányzat (GYMSMO – Local Government of Gyır-Moson-Sopron County)

Árpád u. 32, 9021 Gyır, Hungary

EU Associated 5

Veszprém Megyei Onkormányzat (Krajská rada Veszprém)

Megyeház tér 1. 8200 Veszprém

EU Associated 6

Administratia Rezervatiei Biosferei Delta Dunării (Danube Delta Biosphere Reserve Authority)

Portului 34A, Tulcea, 820243 Romania

EU Associated 7

Fertı-Hanság Nemzeti Park Igazgatóság (Fertö-Hansag National Park)

Rév-Kócsagvár PO.: 4; 9435 Sarród, Hungary

EU Associated 8

Magyar Turizmus Zrt. Közép-dunántúli Regionális Marketing Igazgatóság (Hungarian

Tourism Private Limited Company, Regional Marketing Directorate Central Transdanubia)

Piac tér 12-14, 8000 Székesfehérvár, Hungary

EU Associated 9

Ministerul Dezvoltarii Regionale si Turismului – Direcţia Generală Turistică – Direcţia Dezvoltare Turistică şi Marketing (Ministry of Regional Development and Tourism – General Division for Tourism – Direction for Tourism Development and Marketing)

Str. Apolodor nr. 17, sector 5, 050741 Bucharest, Romania

EU Associated 10

МИЕТ- Министерство на икономиката, енергетиката и туризма

oтдел „Развитие на туристическия продукт”, Дирекция „Туристическа политика”

(Ministry of Economy, Energy and Tourism - Tourism Product Development Department,

Tourism policy Directorate)

SLAVYANSKA STR. 8, Sofia, 1052 Bulgaria

On the basis of:

- COUNCIL REGULATION (EC) No 1083/2006 of 11 July 2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and repealing Regulation (EC) No 1260/1999;

- REGULATION (EC) No 1080/2006 OF THE EUROPEAN PARLIAMENT AND OF THE COUNCIL of 5 July 2006 on the European Regional Development Fund and repealing Regulation (EC) No 1783/1999;

- COMMISSION REGULATION (EC) No 1828/2006 of 8 December 2006 setting out rules for the implementation of Council Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and of Regulation (EC) No 1080/2006 of the European Parliament and of the Council on the European Regional Development Fund;

- COUNCIL REGULATION (EC) No 1085/2006 of 17 July 2006 establishing an Instrument for Pre-accession Assistance (IPA);

-	COMMISSION REGULATION (EC) No. 718/2007 implementing Council Regulation (EC) No.1085/2006 establishing an instrument for pre-accession assistance (IPA);

-	REGULATION (EC) No 1638/2006 OF THE EUROPEAN PARLIAMENT AND OF THE	COUNCIL of 24 October 2006 laying down general provisions establishing a European Neighbourhood and Partnership Instrument;

- the South East Europe Transnational Cooperation Programme, approved by the European Commission on 20 December 2007, Decision No. C(2007)6590; and its amendment approved on 24 March 2011, Decision No. C(2011) 1850

- the SEE Programme Manual (4th  call) and the SEE Implementation Manual laying down the programme specific rules for the implementation of the SEE Projects.

- Article 1

- Definitions

- Lead Partner (ERDF Lead Partner): the Lead Partner is chosen among the Project Partners and has full financial and administrative responsibility for ERDF and IPA contribution for the entire duration of the project. The Lead Partner is also responsible for the proper reporting of progress during project implementation to the Joint Technical Secretariat, as stipulated in the subsidy contract. In principle, the Lead Partner has functional (coordination of the operation’s activities) and financial responsibilities related to ERDF and IPA contribution (corresponds to the term “lead beneficiary” used in the Article 20 of Regulation (EC) No. 1080/2006 and is hereinafter referred to as “LP”).

- Project Partner (ERDF Project Partner / IPA-I Project Partner): an actor which commits himself to implement a project part according to the Application Form as approved by the Monitoring Committee (corresponds to the term “beneficiary” used in the Article 20 of Regulation (EC) No. 1080/2006 and hereinafter referred to as “PP”). The 20% ERDF Project Partner is an ERDF Project Partner from the EU territory but outside the programme area, who participates directly in the project with a separate budget as financial partner.

- ENPI Project Partner: a beneficiary that receives ENPI contribution and complies with ENPI rules.

- Associated Strategic Partner (ASP): fully integrated in the project partnership but with no responsibility of its budget share that is managed by an ERDF “sponsoring” partner: 10% Partner: non-EU partner of the Programme area whose defined costs are paid and validated by an ERDF “sponsoring” partner;
EU Associated 20%: EU partner outside the Programme area whose defined costs are paid and validated by an ERDF “sponsoring” partner; EU Associated: EU partner located in the Programme area whose defined costs are paid and validated by an ERDF “sponsoring” partner.

- Project Participants: means LP, ERDF PPs, IPA-I PPs, ENPI PPs, ASPs.

- Project Part: covers a set of activities undertaken by a Project Partner and presented by an ERDF and IPA-I partner’s budget in the Application Form.

- Article 2

Subject of the Partnership Agreement

- The subject of this Partnership Agreement is the organisation of the partnership by regulating the rights and obligations of all Project Participants in order to successfully implement the transnational project “Sustainable Transport and Mobility in Tourism Regions along the Danube – TRANSDANUBE”.

- The approved Application Form and the subsidy contract will became integral part of this Agreement after the approval of the project by the Monitoring Committee.
The Project Participants have to fully respect the content and obligations set by the abovementioned documents.

- Article 3

Duration of the agreement

- This agreement shall take effect on the date on which it is signed by all Project Participants. It shall remain in force until the LP has discharged in full its obligations arising from the subsidy contract towards the Managing Authority.

- Article 4

Activities of Project Participants in the project

- Activities of the Project Participants as well as the role of each PP in the project are described in the Application Form.

- In case the Project Participants set up a Project Steering Committee, the following rules shall apply:

  - The Project Steering Committee (PSC) shall be composed by respectively one competent representative of all financing project participants and shall be chaired by the LP.

  - Every financing participant will nominee its representative in the PSC and will communicate the name to the Lead Partner.

  - Associated strategic partners shall be invited to take part in the PSC in an advisory capacity. Associated strategic partners have no vote in the PSC.

  - The PSC shall meet on a half-yearly basis ideally at the occasion of regular project partner meetings or additionally on special demand of at least one partner. The SEE Secretariat may be invited to attend meetings, if applicable.

  - The first meeting of the PSC will be convened at the occasion of the kick-off partner-meeting. In this occasion the PSC will be officially formed.

  - The Project Steering Committee:

    - is responsible for the monitoring of the project implementation and project results;

    - monitors the respect of the timing, according to the forecasts established in the Application Form;

    - is invested with the decision-making power and it is convened in occasion of the formal approval of the results of the WPs;

    - is responsible for settlement of any disputes among project participants;

    - can declare a party as a defaulting party and can declare measures related hereto;

    - can set up sub-groups respectively workgroups to deal with specific tasks related to the project.

  - Voting rules and quorum:

    - The PSC shall not deliberate and decide validly unless at least two third of the members are present or represented (quorum).

    - Each member shall have one vote.

    - Defaulting Parties may not vote.

    - Decisions shall be taken by simple majority of the votes.

  - Additional meetings can be held via video-conference. The voting rules above shall apply

  - The work of the PSC is guided by the rules of internal procedures to be agreed upon in the first meeting of the PSC.

- Article 5

Specific obligations of the Lead Partner

- The LP shall take all the steps needed to correctly manage the project in accordance with the Application Form approved by the Monitoring Committee and the subsidy contract.

- In addition the LP shall:

- inform all Project Participants on the signature of the subsidy contract, and provides the copy of the subsidy contract for all Project Participants;

- keep the Project Participants informed on a regular basis about all relevant communication between the LP and Joint Technical Secretariat and LP and Managing Authority;

- inform the Project Participants about all essential issues connected to the project implementation without any delay;

- be responsible for the verification that the expenditure declared by the PPs has been incurred only for the purpose of implementing the project and corresponds to the activities agreed between the PPs in the frame of the approved Application Form;

- be responsible for the verification that the expenditure declared by the PPs and had been validated by the designated Controller at national level;

- submit the Application for Reimbursement together with the Progress Report to the Joint Technical Secretariat for the deadline given in the subsidy contract;

- transfer the ERDF and IPA contribution to the PPs participating in the project according to the Application for Reimbursement approved by the Joint Technical Secretariat, in full and without any delay (within 30 days at the latest) upon receipt of the money at the LP.;

- agree with its PPs before applying for budget reallocation between budget lines and/or work packages in accordance with the subsidy contract;

- agree with the Project Participants (or PPs related to ERDF and IPA issues) of the project before submission of any request for amendment of the subsidy contract to the Joint Technical Secretariat.

- Article 6

- Obligations of the Project Participants and PPs

- The Project Participants respect all the rules and obligations set forth in the subsidy contract.

- They commit themselves to do everything in their power to foster the implementation of the project.

- The Project Participants shall support the LP to fulfil its tasks according to the subsidy contract.

- In particular, each Project Participant shall:

- provide the LP without any delay with any information needed to draw up the Progress Reports and the Final Report, to react on any request by the Managing Authority or the Joint Technical Secretariat, or provide with any further information needed by the LP;

- inform the LP immediately about any circumstance that could lead to a temporary or final discontinuation of the project.

- In particular, each ERDF PP and IPA-I PP shall:

  - maintain either a separate accounting system or an adequate accounting code for all transactions relating to the project;

  - inform the LP on the details of the bank account where the ERDF/ IPA contribution of the PP shall be transferred before the submission of the first Application for Reimbursement,

  - complete their activities foreseen for each reporting period of the project implementation;

  - have their expenditures incurred and paid in the given reporting period validated by the designated Controller of their Member / Partner State and submit the declaration on validation of expenditure issued by the Controller to the LP. The expenditure of the PPs not covered by declarations on validation of expenditure in the given reporting period can be requested only for the next reporting deadline following to the reporting period concerned.

  - comply with Community and national rules, including rules on public procurement, state aid, publicity, rules on environmental protection, and equal opportunities.;

  - be responsible for the sound financial management of the funds allocated to the project part, including the arrangements for recovering amounts unduly paid (ERDF, IPA, state contribution and other public contribution).

- Article 7

Specific obligations of ENPI partners

- The ENPI Project Partners respect all the rules and obligations set forth in the ENPI Grant Contract and related EC and national regulations.

- They commit themselves to complete all activities foreseen for each year of the project implementation.

- ENPI project partner shall be responsible for  the sound financial management of the awarded ENPI grant; and

- Keeping informed the ERDF Lead Partner of the progress of the action and provide all necessary information that the ERDF Lead Partner may require to fulfil its reporting duties towards the SEE JTS.

- Article 8

Specific obligations of the Associated Strategic Partners and the sponsoring ERDF partners

- Each Associated Strategic Partner shall:

- support the “sponsoring” ERDF PP to fulfil its tasks according to the subsidy contract and the present Partnership Agreement;

- complete its activities as described in the approved Application Form;

- provide the “sponsoring” PP and the LP without any delay with any information needed to draw up the Progress Reports and the Final Report, to react on any request by the Managing Authority or the Joint Technical Secretariat, or provide with any further information needed by the LP;

- inform the “sponsoring” ERDF PP and the LP immediately about any circumstance that could lead to a temporary or final discontinuation of the project.

- The expenditure of each Associated Strategic Partner shall:

  - be planned in the budget of the “sponsoring” ERDF LP or ERDF PP in the Application Form;

  - be only those supported by invoices clearly addressed and paid by the “sponsoring” ERDF PP;

  - be validated by the designated controller of the “sponsoring” ERDF PP.

- The Associated Strategic Partners (either 10% Partner or EU Associated 20%) and the “sponsoring” ERDF PPs have to follow the rules for the expenditure under the 10% flexibility rule (10% Partners) or 20% flexibility rule (EU Associated 20%) set by the SEE Programme Manual, in particular:

  - when subcontracting the activities for the involvement of the 10% Partner, the “sponsoring” ERDF PP is responsible for the procurement according to its national public procurement rules. The contents of the terms of reference should be agreed with the 10% Partner;

  - when subcontracting the activities for the involvement of the 10% Partner, the ownership of the outputs and results such as products delivered by the external expertise and services shall remain at the property of the “sponsoring” ERDF PP;

  - the involvement of Associated Strategic Partner (either 10% Partner or EU Associated 20%) for the implementation of the project and the achievements of its objectives has to be clearly demonstrated in the Partner Reports of the „sponsoring” ERDF PP and in the Progress Report of the LP;

  - in instance of 10% Partner participation, the benefit of the EU territory has to be demonstrated in the Application Form as well as during the implementation of the project;

  - in instance of 20% Partner participation, the benefit of the Programme area has to be demonstrated in the Application Form as well as during the implementation of the project;

- The Associated Strategic Partners (either 10% Partner or EU Associated 20%) and the “sponsoring” ERDF PPs have to follow the rules for the expenditure under the 10% flexibility rule (10% Partners) or 20% flexibility rule (EU Associated 20%) set by the SEE Programme Manual.

- Article 9

Responsibilities of LP and ERDF PPs / IPA-I PPs

- The LP solely assumes responsibility for the entire project towards the Managing Authority.

- Each Project Participant is directly and exclusively responsible to the LP for the due implementation of its respective contribution to the project and for the proper fulfilment of its obligations as set out in this agreement. Should a Project Participant not fulfil its obligations under this contract in due time, the LP shall admonish him to fulfil them within a reasonable period of time. The Project Participants will undertake to find a rapid and efficient solution. Should the non-fulfilment continue, the LP may decide to debar the Project Participant concerned from the project with approval of the other Project Participants. The Joint Technical Secretariat shall be promptly informed of such an intended decision by the LP and the change in the partnership has to be approved by the Monitoring Committee according to the provisions of the subsidy contract.

- Each PP shall take the financial responsibility for the ERDF and IPA contribution and the related state contribution it has received for the project.

- In case of irregularities the LP bears the overall responsibility towards the Managing Authority for the repayment of the amounts unduly paid. By way of the derogation from this principle if the irregularity is committed by a PP the concerned PP shall repay to the LP the amounts unduly paid.

- Article 10

Reporting obligations of the PPs

- The LP can only submit an application for reimbursement to the Joint Technical Secretariat by providing proof of progress of the project. Therefore, in order to provide adequate information on the progress of the project, each PP has to submit a Partner Report to the LP consisting of an activity report describing the activities carried out and their outputs and results during the reporting period and a financial report presenting the financial progress of the project in accordance with the approved Application Form.

- The PPs have to respect the reporting deadlines of the subsidy contract, and submit their ERDF / IPA Partner Report and declaration on validation of expenditure to the LP in due time, until 6 weeks before the relevant reporting deadline. Partner Reports and declarations on validation of expenditure not submitted to the LP within the set deadline will not be included in the progress report of the LP to be submitted to the JTS.

- The Partner Reports should be drawn up in Euro. In case PPs from Member States which have not adopted the Euro as their currency are participating in the project, as well as in case of IPA Partner States, the PPs shall convert into Euro the amounts of expenditure in the list of invoices incurred in national currency before submission for validation to the responsible controller of the Member State/Partner State. The expenditures shall be converted into Euro using the monthly accounting exchange rate of the Commission in force in the last month of the reporting period. (http://ec.europa.eu/budget/inforeuro/index.cfm?Language=en)
The exchange rate risk is borne by the PP concerned.

- Article 11

Audits

- For audit purposes each ERDF PP – IPA-I PP shall:

- retain all files, documents and data about the project at least until 31 December 2022, either in original or as certified copies on commonly used data media safely and orderly;

- enable the responsible auditing bodies of the European Union and the auditing bodies of the state it is based in to audit the proper use of funds;

- give these authorities any information about the project they request;

- give them access to the accounting books and accounting documents and other documentation related to the project, whereby the auditing bodies decide on this relation, at least until 31 December 2022;

- give them access to their business premises during the ordinary business hours and also beyond these hours by arrangement and allow them to carry out checks related to the project at least until 31 December 2022;

- provide the LP with any information needed related to such an audit without any delay.

- Article 12

Information and Publicity

- Any publicity measure undertaken by any of the Project Participants shall be conducted according to the Commission Regulation (EC) no. 1828/2006, and the Information and Publicity guidelines of the SEE Programme.

- Information and publicity measures will be coordinated among the Project Participants. Each Project Participant is equally responsible to promote the fact that financing is provided from the European Union funds in the framework of the South East Europe Transnational Cooperation Programme and to ensure the adequate promotion of the project.

- The Project Participants take note of the fact that the results of the project as well as any study or analysis produced in the course of the project will be made available to the public and they agree that the results of the project shall be available for all Project Participants and for the public free of charge.

- Article 13

Changes in the Project Partnership

- Being aware of the fact that all changes in the partnership need an approval of the Monitoring Committee and the Managing Authority is entitled to withdraw from the subsidy contract if the number of Project Participants falls below the minimum number of participants required by the programme, the Project Participants agree not to back out of the project unless there are unavoidable reasons for it.

- In case a Project Participant withdraws from the project or is debarred from it the remaining Project Participants will undertake to find a rapid and efficient solution to ensure the further proper project implementation without any delay. Consequently, the Project Participants will endeavour to cover the contribution of the withdrawing Project Participant, either by assuming its tasks by one or more of the present Project Participants or by asking one or more new participants to join the project partnership, regarding the respective programme provisions.

- The LP will inform the Joint Technical Secretariat as soon as changes in the project partnership are foreseeable. The changes in the partnership enter into force only after approval by the Monitoring Committee.

- The provisions set for audits in Article 11 remain applicable to the PP that backed out of the project or was debarred from the project.

- Article 14

Irregularities and repayment of funds (ERDF / IPA)

- If the Managing Authority should – based on the provisions of the subsidy contract – request the repayment of ERDF / IPA contribution from the LP, the LP shall ask the PP that has caused the irregularity resulting in repayment of the ERDF / IPA contribution unduly paid according to the request of the Managing Authority.

- The PP affected has to repay the requested ERDF / IPA contribution together with the interests chargeable to the LP, and the corresponding state contribution to the responsible national body as stipulated in the contract on the state contribution.

- The PP has to respect the deadline given by the Managing Authority to the LP for the repayment of ERDF / IPA contribution. The PP has to transfer the requested ERDF / IPA contribution together with the interests chargeable to the LP 30 days before the deadline of the LP.

- In the case that no project participant can be held responsible for the request for repayment, the amount requested shall be apportioned between all project participants pro rata to their project share (meaning the amount of ERDF-funds they have been granted according to the approved application form).

- Article 15

- Cooperation with third parties, assignment

- In case of cooperation with third parties (e.g. concluding subcontracts) the ERDF / IPA-I Project Participant shall remain the sole responsible toward the LP concerning compliance with its obligations as set out in this agreement.

- ERDF / IPA-IProject Participants are allowed to assign their rights and obligations under this agreement with prior consent of the other Project Participants and only after prior written consent of the Managing Authority and the Monitoring Committee.

- In case of legal succession, e.g. when the Project Participant changes its legal form, the Project Participant is obliged to transfer all duties under this contract to the legal successor. The participant shall notify the LP in written form within 30 days.

- Article 16

Language

The working language of the partnership shall be English. Any official internal document of the operation shall be made available in the language of the subsidy contract, i.e. in English.

- Article 17

Applicable law

1.	This agreement is governed by the Austrian law, being the law of the country of the LP.

2.		This partnership agreement is concluded in English. In case of a translation of this agreement and its annexes into another language than English, the English version shall prevail.

- Article 18

Concluding provisions

1.		Any amendments to this agreement shall be in writing signed by all Project Participants.

2.	Amendments and supplements to the present agreement and any waiver of the requirement of the written form must be in written form and have to be indicated as such. The LP shall notify to the Joint Technical Secretariat of any amendment or supplement of the present agreement.

3.	If any provision in this agreement should be wholly or partly ineffective, the remaining provisions remain binding for the parties. In this case the parties undertake to replace the ineffective provision by an effective one which comes as close as possible to the purpose of the ineffective one.

4.	The LP and all the Project Participants commit themselves to taking measures to ensure that all staff members carrying out the work respect the confidential nature of information regarded as such, and do not disseminate it, pass it on to third parties or use it without prior written consent of the LP and the Project Participant that provided the information.

5.	The parties will make an effort to settle any disputes arising from this agreement out of the court. In case an agreement cannot be made in due time, the parties herewith agree that Vienna shall be the venue for all legal disputes arising from this contract.

6. 	25 original copies will be made of this agreement; of which each party keeps one original and one original is attached to the Application Form.

- Project Participant

- DIE DONAU - Internationale Touristische Werbegemeinschaft (Danube Tourist Commission)

- Name of legal responsible: Gerd Skoff

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

- Amt der Burgenländischen Landesregierung (Regional Government of Burgenland)

- Name of legal responsible: Peter Zinggl

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

- Bratislavský samosprávny kraj (Bratislava Self-Governing Region)

- Name of legal responsible: Ing. Pavol Frešo

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Nyugat-Pannon Terület- és Gazdaságfejlesztési Szolgáltató Nonprofit Kft. (West Pannon Regional and Economic Development Nonprofit Ltd.)

Name of legal responsible: Eszter, VARGA

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

BBTDM, Bakony és Balaton Térségi Turisztikai Nonprofit Korlátolt Felelősségű Társaság (Bakony and Balaton Regional Tourism Nonprofit Ltd)

- Name of legal responsible: Tamara Lencsés

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

- Областна администрация Видин (Vidin Regional Administration)

- Name of legal responsible: Tsvetan Asenov

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Клуб „Устойчиво развитие на гражданското общество” (Club Sustainable Development for Civil Society)

- Name of legal responsible: Prof. Lucia Ilieva

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Institutul National de Cercetare-Dezvoltare in Turism (National Institute for Research and Development in Tourism)

- Name of legal responsible: Ovidiu Teodorescu

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

ADRSE - Agentia pentru Dezvoltare Regionala a Regiunii de Dezvoltare Sud-Est, (SE RDA – The Regional Development Agency of the South-East Development Region)

- Name of legal responsible: Luminita MIHAILOV

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Slovensky Cykloklub  	
(Slovak Cycle Club)

Name of legal responsible: Dr Juraj Hlatky, Chairmen

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

Project Participant

Donaubüro gemeinnützige GmbH (Danube Office Ulm Ltd.),

Name of legal responsible: Gunter Czisch

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

RARIS-Regionalna agencija za razvoj istocne Srbije 	
(Regional Development Agency Eastern Serbia)

- Name of legal responsible: Vladan Jeremić

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

- Dunavski centar za kompetenciju (Danube Competence Centre)

- Name of legal responsible: Boris Čamernik

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Stadtgemeinde Neusiedl am See (Municipality Neusiedl am See)

Name of legal responsible: Kurt Lentsch

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Ministerstvo dopravy, výstavby a regionálneho rozvoja Slovenskej republiky (Ministry of Transport, Construction and Regional Development of the Slovak Republic)

Name of legal responsible: Ing. Martin Čatloš

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Regionálna rozvojová agentúra Senec – Pezinok 	
(Regional Development Agency Senec Pezinok)

Name of legal responsible: Dipl. Ing. Luba Pavlovová

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

GYMSMÖ – Győr-Moson-Sopron Megyei Önkormányzat (GYMSMO – Local Government of Győr-Moson-Sopron County)

Name of legal responsible: Dr. Imre Szakács

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Veszprém Megyei Önkormányzat (Veszprém County Council)

Megyeház tér 1., 8200 Veszprém

Name of legal responsible:

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Fertő-Hanság Nemzeti Park Igazgatóság (Fertö-Hansag National Park)

Rév-Kócsagvár PO.: 4; 9435 Sarród, Hungary

Name of legal responsible:  Gábor Reischl

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Administratia Rezervatiei Biosferei Delta Dunării (Danube Delta Biosphere Reserve Authority)

Portului 34A, Tulcea, 820243 Romania

Name of legal responsible:

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Magyar Turizmus Zrt. Közép-dunántúli Regionális Marketing Igazgatóság (Hungarian

Tourism Private Limited Company, Regional Marketing Directorate Central Transdanubia)

Piac tér 12-14, 8000 Székesfehérvár, Hungary

Name of legal responsible: Laszlo Bodrogai

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

Ministerul Dezvoltarii Regionale si Turismului – Direcţia Generală Turistică – Direcţia Dezvoltare Turistică şi Marketing (Ministry of Regional Development and Tourism – General Division for Tourism – Direction for Tourism Development and Marketing)

Str. Apolodor nr. 17, sector 5, 050741 Bucharest, Romania

Name of legal responsible: Elena Gabriela Udrea

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp

- Project Participant

МИЕТ- Министерство на икономиката, енергетиката и туризма

oтдел „Развитие на туристическия продукт”, Дирекция „Туристическа политика”

(Ministry of Economy, Energy and Tourism - Tourism Product Development Department,

Tourism policy Directorate)

SLAVYANSKA STR. 8, Sofia, 1052 Bulgaria

Name of legal responsible:

Place, Date:

Signature:

Stamp

- Lead Partner

- Umweltbundesamt GmbH (Environment Agency Austria)

- Name of legal responsible: Georg Rebernig

Place, Date: Vienna,

Signature:

Stamp